## Sheet1
| TASK | Responsible | Who needs to be involved | Due | Comments |  | Is this a ROTAN modelling task?
General
| Confirm Gorse avaliability and target | Helen | Richard | 2014-06-01 | Note: need to consider was gorse included in the 746 load and does it matter if less than 30 T N? (Yes we believe this is included but it is not specifically identified as a line item) |  | no
| Confirm position on house lots, including sewerage disposal | Stephen |  | 2015-04-15 |  |  | no
| Spreadsheet “adjustments” – documentation of what they are and why they were done. Do these feed into re-running the methodology? | Alastair | Michelle, Kit |  | Define the method used to define the land use that has not been BMed(Michelle), This includes some land areas inside GNS bdy, non-Bmed areas and <40 Ha, and areas outside the BOP. Need to have ion BM's rules posiution not clear. (Road berms and parks etc). | Could be probglem getting support from Michelle due to GIS constraints | yes
| Agreement on numbers (Warwick’s idea of fixing points where we can and form an agreed position) | Stephen | Alastair/Simon | Need to await ROTAN results to provide final non-attenuated figures | Relate to the integrated framework numbers, 140 -->100t and then convert to unattenuated. |  | no
| Advice and recommendation on consistent methodology to amend Nitrogen targets as a result of Overseer version changes throughout the life of the rules | Stephen | Andy, Alastair, Lisa and Simon | Mid-May | This may be difficult to achieve and consider the possibility of leaving this for several years. |  | no
| Get agreement on the correct protocols for Overseer V6.2 (Or assess the difference between 6.13 and 6.2) | Alastair |  | Mid-May depending on AgRes availability | May need to get guidance from AgRes and other experts locally. | Need to confirm AgRes availability to assist this work | yes
| Transition BM files to V 6.2 (This depends on the sensitivity of 6.13/6.2 conversion). | Alastair | TBA | 30 June if resources are allocated. | May need database assistance to stream line this. May need consultant support to do the transition? | Need to check availability of Derek to assit in batabase matters. | yes
| ROTAN definitons of land categories: amalgamate ROTAN and BM spacial definitions to coincide. | Andy/David | Alastair/Michelle/Kit? | 2015-06-30 | Need consisitant and repeatable definitions of areas in the catchment. Aimfor ROTAN to adopt BM definitios | Need to discuss with David as model development progresses | yes
1 | Status Quo Annual Catchment Nitrogen Budget (based on mid-2001 to mid-2004 Rule 11 Benchmark Data in Overseer v6.1.3) accounting for: | ROTAN
1a | The groundwater catchment defined by the 'best estimate' from the 2014 GNS Report | Stephen | Alastair/Simon | End April | Decide and adopt the GNS maps (yes/no). Is BM/non-BM another line? The GW boundary is simply a map, do we need to get correct scale completed?
1b | All diffuse and point source N discharges to land and water (including land use sector breakdown consistent with the draft rules). Catchment Budget? | Andy | Simon/Alastair/David | Mid-May | Add point source info. 2001-2004, allow attenuated and non-attenuated eg Tikitere Is this ROTAN also? | Input new Tikitere numbers, say 40t N, and understand the septic tankinputs (ie keep note of method for calculation of inputs).
1c | N attenuation rates between various discharges and the lake | Alastair | Kit/Simon/Andy | Mid-May | Kit and TAG advice | Need to check Kit availability to support these tasks
1d | Source/sector breakdown of attenuated N discharge to the lake ie ROTAN output in table form. | David | Kit/Alastair/Andy | 2015-07-30 | Kit and TAG advice | See Alastair for times
2 | Proposed 2032 Annual Catchment Nitrogen Budget accounting for: | ROTAN |  |  |  | Confirm with David timeframes for scenario outputs once model calibrated.
2a | All attenuated diffuse and point source N discharges (using 2001-2004 land use areas) and identifying: | Covered below
2.a.i | A N scenario that meets the target N Load (to the lake) from all non-pastoral sources, incorporating reductions from gorse and engineering interventions based on the latest avaliable estimates provided by the Lakes Programme. | Andy/David | Niroy/Andy WH/Greg Manzano | Mid-May | Need input from RLC re sewage inputs. Need to consider the impact of gorse in the model, may need to do 2 scenarios with it in and out.
2.a.ii | A N scenario that meets the target N Load (to the lake) from land that was pastoral use (2001-2004), based on requiring the annual load from all sources to sum to 435tN/yr. | Andy/David | David/Alstair/Simon | 2015-07-30 | This requires a run of ROTAN that will not be available until 30 June 2015.
2b | The non-attenuated discharge from land that was in pastoral use during 2001-2004, corresponding to the attenuated load in 2.a.ii. | Andy/David | David/Alstair/Simon | 2015-07-30 | This requires a run of ROTAN that will not be available until 30 June 2015.
2c | A table focussing on land in pastoral use during 2001-2004, comparing: | Covered below
2.c.i | The attenuated N load to the lake in the status quo scenario and in the 2032 scenario | Andy/David | David/Alstair/Simon | 2015-07-30 | This is compiling a table that will come from the ROTAN model runs
2.c.ii | The attenuated combined pastoral loads used in developing the Integrated Framework (status quo of 526 tN/yr, a reduction of 240 tN/yr and a target of 286 tN/yr). | Developed above in 2.c.i
2d | A table showing the proposed NDA levels applied to dairy and drystock land to give non-attenuated sectoral N discharges. | Andy/David | David/Alstair/Simon | 2015-07-30 | From above calculation
3 | A proposed 2022 Annual Catchment Nitrogen Budget | ROTAN
3a | Review 2022 reduction amounts to be consistent with the science approach outlined above for the status quo and 2032 catchment N budgets: | Covered below |  |  | This has been set by the policy, the science just needs to identify land use scenario that will achieve the taget of 70% set.
3.a.i | Expected 2022 in-lake loads using the latest estimate for gorse and engineering projects (as above). | Andy/David | David/Alastair/Simon | 2015-07-30
3.a.ii | A calculation of attenuated and non-attentuated N load from pastoral sources (2001-2004 land use areas) that will be reuqired to achieve 70% of the 311tN/yr reduction anticipated by the RPS. | Andy/David | David/Alastair/Simon | 2015-07-30
4 | ROTAN ? |  |  |  | ROTAN will not be available until 30 June so is there a need to do some spread sheet calcs before then? Note that the scenarios will only be run after 30 June.
Lisa may need info to support the rules by Mid-May for the Council agenda.
Note on B6: Helen Creagh: Is this the spreadhseet that Simon was talking about?
Note on B7: Helen Creagh: Isn't this status quo as set out below?
Note on B36: Helen Creagh: Not sure exactly what is required here - is it a reccomendation on whether or not to continue with ROTAN?

## Sheet2
output needed
Nitrogen source | Status Quo |  | 2022 |  | 2033
| Unattenuated load inputs | Attenuated load outputs to the lake | Unattenuated load inputs | Attenuated load outputs to the lake | Unattenuated load inputs | Attenuated load outputs to the lake
sewage
rainfall
dairy
sheep/beef
urban
lifestyle
etc
Total |  | 435 T